## Cummulative
Sprint 3 | [5 empty] | Cummulative | [5 empty] | Cummulative
Day | Story Points | Completed Story Points | Story Points in Sprint Backlog | Ideal Story Points |  | Day | Story Points Completed (Per Day) | Completed Story Points | Total Story Points | Ideal Story Points |  | Day | Story Points | Completed Story Points | Total Story Points | Ideal Story Points
2023-02-15 | 0 | 0 | 44 | 0 | Sprint 1 | 2023-01-18 | 0 | 0 | 155 | 0 | Sprint 1 | 2023-01-17 | 0 | 0 | 97 | 0
2023-02-17 | 5 | 5 | 44 |  |  | 2023-01-20 | 22 | 22 | 155 |  |  | 2023-01-20 | 22 | 22 | 97
2023-02-20 | 5 | 10 | 44 |  |  | 2023-01-23 | 13 | 35 | 155 |  |  | 2023-01-22 | 13 | 35 | 97
2023-02-22 | 13 | 23 | 44 |  |  | 2023-01-25 | 9 | 44 | 155 |  |  | 2023-01-24 | 9 | 44 | 97
2023-02-24 | 8 | 31 | 44 |  |  | 2023-01-27 | 23 | 67 | 155 |  |  | 2023-01-27 | 23 | 67 | 97
2023-02-27 | 8 | 39 | 44 | 44 |  | 2023-01-30 | 20 | 87 | 155 |  |  | 2023-01-30 | 20 | 87 | 97
[5 empty] | Sprint 2 | 2023-02-01 | 5 | 92 | 175 |  | Sprint 2 | 2023-02-01 | 5 | 92 | 153
[6 empty] | 2023-02-03 | 6 | 98 | 175 |  |  | 2023-02-03 | 6 | 98 | 153
[6 empty] | 2023-02-06 | 11 | 109 | 175 |  |  | 2023-02-06 | 11 | 109 | 153
[6 empty] | 2023-02-08 | 9 | 118 | 175 |  |  | 2023-02-08 | 9 | 118 | 153
[6 empty] | 2023-02-10 | 8 | 126 | 175 |  |  | 2023-02-10 | 8 | 126 | 153 |  | 3
[6 empty] | 2023-02-13 | 14 | 140 | 175 |  |  | 2023-02-13 | 14 | 140 | 153 |  | 2
[5 empty] | Sprint 3 | 2023-02-15 | 0 | 140 | 195 |  | Sprint 3 | 2023-02-15 | 0 | 140 | 179 |  | 5
[6 empty] | 2023-02-17 | 5 | 145 | 195 |  |  | 2023-02-17 | 2 | 142 | 179 |  | 3
[6 empty] | 2023-02-20 | 5 | 150 | 195 |  |  | 2023-02-20 | 5 | 147 | 179 |  | 3
[6 empty] | 2023-02-22 | 13 | 163 | 195 |  |  | 2023-02-22 | 13 | 160 | 179 |  | 5
[6 empty] | 2023-02-24 | 8 | 171 | 195 |  |  | 2023-02-24 | 8 | 168 | 179 |  | 5
[6 empty] | 2023-02-27 | 8 | 179 | 195 | 195 |  | 2023-02-27 | 8 | 176 | 179 | 179 | 3
8
5
3
1
5
8
8
5
5
8
2
3
3
3
8
5
[17 empty] | 3 | 131
5
5
3
5
1